## Slide 1
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Defining and Sequencing Activities:
Introduction: To effectively manage a project, it’s crucial to clearly define and sequence the activities that need to be completed. This ensures that tasks are organized logically and efficiently, laying the foundation for accurate scheduling.

## Slide 2
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Defining and Sequencing Activities:
Practical Scenario Presentation: Imagine you’re working on a project for Atlassian to develop a new software tool. Your team needs to outline all the activities required, from initial concept design to final testing. You must also determine the order in which these tasks should be executed.
Class Discussion Question: If you were in charge of this project, how would you prioritize and sequence the activities? Which tasks would you need to complete first, and why?

## Slide 3
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Defining and Sequencing Activities:
Responses: You might suggest starting with the concept design, followed by requirement gathering, then development, testing, and finally deployment. Understanding dependencies between tasks would help you determine the correct sequence.
Multiple-Choice Question: Which of the following is the first step in Project Time Management?
a) Estimating Duration b) Defining and Sequencing Activities c) Schedule Control d) Developing the Schedule

## Slide 4
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Estimating Duration Techniques:
Introduction: Estimating how long each task will take is crucial for developing a realistic project schedule. Various techniques can be used, depending on the level of detail available and the complexity of the project.

## Slide 5
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Estimating Duration Techniques:
Practical Scenario Presentation: You are managing a construction project for Lendlease. You need to estimate the duration of various tasks like foundation laying, framing, and roofing. You have previous data from similar projects but need to adjust for current conditions.
Class Discussion Question: Which estimating technique would you use for this project, and why? Would you prefer expert judgment, analogous estimating, or a more detailed parametric analysis?

## Slide 6
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Estimating Duration Techniques:
Responses: You might prefer expert judgment if you have experienced team members, or analogous estimating if you have relevant historical data. Parametric analysis could be useful if you need precise estimates based on quantifiable factors.
Multiple-Choice Question: Which of the following techniques is based on historical data from similar projects?
a) Analogous Estimating b) Expert Judgment c) Three-Point Estimating d) Parametric Estimating

## Slide 7
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Developing the Schedule
Introduction: Once activities are defined, sequenced, and their durations estimated, the next step is to develop the project schedule. This involves creating a timeline that reflects the planned start and finish dates for each activity.

## Slide 8
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Developing the Schedule
Practical Scenario Presentation: As a project manager at Telstra, you need to develop a schedule for rolling out a new nationwide broadband service. The project has multiple dependencies and requires coordination across various teams.
Class Discussion Question: What factors would you consider when developing the project schedule, and how would you manage dependencies and resource constraints?

## Slide 9
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Developing the Schedule
Responses: You might consider factors such as task dependencies, resource availability, and potential bottlenecks. Utilizing software tools like MS Project or Primavera could help you visualize and adjust the schedule as needed.
Multiple-Choice Question: What is the primary output of the Develop Schedule process?
a) Project Charter b) Resource Calendar c) Work Breakdown Structure
d) Project Schedule

## Slide 10
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Schedule Control
Introduction: Once the schedule is developed and the project is underway, it’s important to monitor progress and control the schedule. This ensures that the project stays on track and any deviations are managed effectively.

## Slide 11
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Schedule Control
Practical Scenario Presentation: You’re overseeing the development of a new mobile app for Commonwealth Bank. Midway through the project, you discover that some key milestones are slipping. You need to implement schedule control measures to get the project back on track.
Class Discussion Question: What steps would you take to control the schedule and bring the project back on track? Would you fast-track, crash, or re-baseline the schedule?

## Slide 12
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Schedule Control
Responses: You might consider fast-tracking to run activities in parallel or crashing by adding resources to critical tasks. Re-baselining could be necessary if the project scope has changed significantly.
Multiple-Choice Question: Which of the following is a technique used to bring a delayed project back on track?
a) Crashing b) Sequencing c) Parametric Estimating d) Analogous Estimating

## Slide 13
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Summary:
In Project Time Management, defining and sequencing activities, estimating durations, developing the schedule, and controlling the schedule are crucial steps that ensure the timely completion of projects. Each step involves specific techniques and considerations that help manage the project's timeline effectively.

## Slide 14
08
Group Class Activity 1 – Defining and Sequencing Activities - Project Simulation Calibri Size 28: Fkeivanian@my.holmes.edu.au
Objective: To engage students in the practical application of defining and sequencing project activities.
Instructions:
Each group selects a fictional project (e.g., developing a mobile app for a start-up, launching a marketing campaign for a new product, etc.).
Each group must define all the activities required to complete their project and determine the correct sequence for these activities.
Once completed, each group will present their activity list and sequence to the class, explaining the rationale behind their choices.
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian

## Slide 15
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Discussion Question: What challenges did you face in defining and sequencing the activities, and how did you overcome them?
Outcome: Students will gain hands-on experience in organizing project tasks, and the discussion will highlight the importance of understanding dependencies between tasks.
Group Class Activity 1 – Defining and Sequencing Activities - Project Simulation Calibri Size 28: Fkeivanian@my.holmes.edu.au

## Slide 16
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Objective: To practice different techniques for estimating the duration of project activities.
Instructions:
Provide each group with a set of project tasks related to a fictional construction project.
Ask each group to use different estimation techniques (e.g., expert judgment, analogous estimating, parametric estimating) to estimate the duration of these tasks.
Groups should compare their results and discuss the pros and cons of each technique.
Group Class Activity 2 – Estimating Duration Techniques - Estimation Workshop Calibri Size 28: Fkeivanian@my.holmes.edu.au

## Slide 17
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Discussion Question: Which estimation technique did your group find most reliable, and why? How did the techniques differ in terms of accuracy and ease of use?
Expected Outcome: Students will understand the application and effectiveness of different estimation techniques and learn how to choose the most appropriate one based on project requirements.
Group Class Activity 2 – Estimating Duration Techniques - Estimation Workshop Calibri Size 28: Fkeivanian@my.holmes.edu.au

## Slide 18
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Objective: To develop a project schedule considering task dependencies, resource constraints, and potential risks.
Instructions:
Each group is tasked with developing a schedule for a fictional project (e.g., organizing a company event, implementing a new IT system).
Provide groups with a set of predefined tasks, resources, and potential risks (e.g., limited availability of key personnel, unexpected delays).
Groups must create a detailed schedule, using tools like Gantt charts if available, and consider how to handle dependencies and resource constraints.
Group Class Activity 3 – Developing the Schedule - Interactive Scheduling Challenge Calibri Size 28: Fkeivanian@my.holmes.edu.au

## Slide 19
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Discussion Question: What strategies did your group use to manage dependencies and resource constraints? How did you account for potential risks in your schedule?
Expected Outcome: Students will experience the complexities of scheduling in real-world projects and learn how to manage constraints and risks effectively.
Group Class Activity 3 – Developing the Schedule - Interactive Scheduling Challenge Calibri Size 28: Fkeivanian@my.holmes.edu.au

## Slide 20
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Objective: To simulate real-world scenarios where the project schedule is at risk and practice schedule control techniques.
Instructions:
Present each group with a crisis scenario where a critical project task is delayed (e.g., a key supplier is late, a team member is unavailable).
Groups must decide on the best schedule control technique to address the delay (e.g., fast-tracking, crashing, re-baselining).
Each group presents their chosen solution and explains how they would implement it to bring the project back on track.
Group Class Activity 4 – Schedule Control - Crisis Management Simulation Calibri Size 28: Fkeivanian@my.holmes.edu.au

## Slide 21
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Discussion Question: Which schedule control technique did your group choose, and why? How would you mitigate the impact of the delay on the overall project timeline?
Expected Outcome: Students will learn how to apply schedule control techniques in challenging situations and understand the importance of flexibility and decision-making in project management.
Group Class Activity 4 – Schedule Control - Crisis Management Simulation Calibri Size 28: Fkeivanian@my.holmes.edu.au

## Slide 22
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Group Class Activity 4 – Schedule Control - Crisis Management Simulation Calibri Size 28: Fkeivanian@my.holmes.edu.au
Project Management Tools
Gantt Chart in Asana: https://www.youtube.com/watch?v=pwiKrbnytWg
Gantt Chart in MS Excel: https://www.youtube.com/watch?v=zC22yPmc6Kw
Tutorial on Trello: https://www.youtube.com/watch?v=sC6UwpVEEE0
Gantt Chart in Trello: https://www.youtube.com/watch?v=JEGMROCxAJk
Gantt Chart in MS Project: https://www.youtube.com/watch?v=uqo5DLD-ssI

## Slide 23
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Asana Gantt Chart
Regardless of whether you’re working as a freelancer or in a team, one of the most useful ways to organize your project tasks is by using an Asana Gantt chart. Asana is a browser-based task and to-do list manager that lets you do different projects with different deadlines, complications, and timelines.
A Gantt chart is a graphic representation of a project’s schedule as a time-phased bar chart. It is named for its creator, Henry Gantt, a U.S. mathematician and creator of the earliest modern project scheduling system. It is a disciplined project-management tool that involves identifying tasks, assigning resources, and assigning timelines and milestones to the tasks.

## Slide 24
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Asana Gantt Chart
Project managers can plan their work and determine a project’s timetable, thanks to Asana Gantt Charts. Project scheduling can assist teams in organizing themselves to meet deadlines and provide quality work.
The length of a bar in a Gantt chart denotes the time needed to accomplish a task, and each bar represents a phase of the project (or task within a project). The Asana Gantt chart gives you a comprehensive perspective of the workflow so that management can monitor each task and assign it the appropriate priority.

## Slide 25
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Asana Gantt Chart
Step 1: Set Up a Project in Asana
Log in to Asana: Navigate to asana.com and log in or create an account.
Create a New Project:
  Click on the “+” button or the “Create New Project” option.
  Choose a template or start with a blank project.
  Name your project and set up your preferred layout (list or board).
  Screenshot: Capture the screen where you create a new project.

## Slide 26
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Asana Gantt Chart
Step 2: Add Tasks to Your Project
Create Tasks:
  Click the “Add Task” button to start adding tasks to your project.
  Name your tasks, which represent different phases or activities.
  Screenshot: Capture the screen after you've added a few tasks.
Assign Dates:
  Open a task and set a start date and a due date.
  Screenshot: Capture the screen where you're assigning dates to a task.
Assign Responsibilities:
  Assign the task to a team member.
  Screenshot: Capture the screen where you're assigning a team member to a task.

## Slide 27
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Asana Gantt Chart
Step 3: Switch to Timeline View (Gantt Chart)
Access Timeline View:
  In your project, click on the “Timeline” tab to view the Gantt chart.
  Screenshot: Capture the Timeline view screen.
Adjust the Timeline:
  Drag and drop tasks to adjust start and end dates directly in the Timeline view.
  Screenshot: Capture a screen showing tasks being moved on the Timeline.

## Slide 28
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Asana Gantt Chart
Step 4: Add Milestones and Dependencies
Create Milestones in Timeline View:
Access Timeline View:
  Navigate to your project and click on the “Timeline” tab (you've already done this in Step 3).
Add a Milestone:
  In the Timeline view, look for the “+” button or “+ Milestone” option usually located at the top or side of the timeline view.
  Click on “+ Milestone.” This will allow you to create a new milestone directly within the Timeline view.
  Name Your Milestone: Enter a name for the milestone to represent a key checkpoint or goal in your project.
  Set the Date: Choose a specific date for the milestone by clicking on the date field associated with it. Milestones are single-date items, so you only need to set the due date.
  Screenshot: After adding the milestone, capture the screen to show the new milestone added in the Timeline.

## Slide 29
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Asana Gantt Chart
Set Dependencies Between Tasks:
Select a Task:
  Click on the task that needs to be dependent on another task.
Drag the Connector:
  Look for a small circle on either end of the task bar in the Timeline view. This is the dependency handle.
  Click and Drag: Click on the circle and drag it to another task that should be a prerequisite or a subsequent step.
  Release the drag when you’ve connected the two tasks. This will create a dependency line between the tasks, indicating that one task depends on the completion of the other.
  Screenshot: Capture the screen showing the linked tasks with the dependency line between them.

## Slide 30
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Asana Gantt Chart
Milestones are used to mark significant points in your project, and they are shown as diamond-shaped icons in the Timeline view.
Dependencies help you define the order in which tasks should be completed. Tasks that are dependent on each other will be connected with lines in the Timeline view.

## Slide 31
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Asana Gantt Chart
Step 5: Customize and Export
Customize the View:
  Adjust the zoom level to see more or less of your project timeline.
  Screenshot: Capture a screen showing different zoom levels or filter settings.
Export the Gantt Chart:
  Click on the “...” (More Options) in the top right corner of the Timeline view.
  Choose “Export/Print” to download the chart as a PDF or CSV file.
  Screenshot: Capture the screen where you choose to export or print.

## Slide 32
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Suggested Project Topics for Gantt Chart Creation:
1. Event Planning
  Description: Plan a corporate conference or workshop, including tasks like booking the venue, arranging speakers, marketing the event, and managing registrations.
  Key Tasks: Venue booking, Speaker coordination, Marketing campaign, Registration management, Event day logistics.
2. Software Development
  Description: Develop a simple mobile or web application, from concept to deployment.
  Key Tasks: Requirement gathering, Design, Development, Testing, Deployment, User training.

## Slide 33
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Suggested Project Topics for Gantt Chart Creation:
3. Product Launch
Description: Organize the launch of a new product in the market, including market research, production, and marketing efforts.
Key Tasks: Market research, Production, Packaging design, Marketing campaign, Launch event, Post-launch analysis.
4. Marketing Campaign
Description: Plan and execute a marketing campaign for a new or existing product or service.
Key Tasks: Campaign planning, Content creation, Social media marketing, Email marketing, Ad placements, Campaign analysis.

## Slide 34
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Suggested Project Topics for Gantt Chart Creation:
5. Construction Project
Description: Manage the construction of a small building or renovation project, from planning to completion.
Key Tasks: Site preparation, Foundation laying, Framing, Electrical and plumbing installation, Roofing, Interior finishing.
6. Research Project
Description: Conduct a research project, such as a scientific study or market research, including data collection, analysis, and reporting.
Key Tasks: Literature review, Hypothesis formulation, Data collection, Data analysis, Report writing, Publication submission.

## Slide 35
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Suggested Project Topics for Gantt Chart Creation:
7. Community Service Project
Description: Plan and implement a community service project, such as organizing a charity event or environmental cleanup.
Key Tasks: Project planning, Volunteer coordination, Resource allocation, Event execution, Post-event reporting.
8. Educational Course Development
Description: Develop an online or in-person educational course, including curriculum design, content creation, and course delivery.
Key Tasks: Curriculum design, Content development, Platform setup, Student enrollment, Course delivery, Feedback collection.

## Slide 36
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Reasons for Using a Software Tool:
Visual Representation: Tools like MS Project or Asana provide a visual representation of the project schedule, making it easier to understand task dependencies, resource allocation, and the overall project timeline.
Automated Calculations: These tools can automatically calculate durations, critical paths, and potential delays, reducing the likelihood of errors that can occur with manual calculations.
Scenario Planning: Software tools allow students to simulate different scenarios (e.g., what happens if a task is delayed?) and see the impact on the overall project, helping them understand the importance of schedule control.
Collaboration: These tools often include features for collaboration, enabling group work to be more effective as students can share project plans, updates, and feedback in real-time.

## Slide 37
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
Specific Activities and Recommended Tools:
Defining and Sequencing Activities: Students can use Gantt charts in ASANA, MS Project or similar software to sequence tasks visually.
Estimating Duration Techniques: Software tools can help apply different estimation techniques and compare the results effectively.
Developing the Schedule: Students can develop a detailed schedule using MS Project, which helps in managing task dependencies and resources.
Schedule Control: Tools like Primavera can simulate the impact of schedule control techniques such as fast-tracking or crashing, allowing students to understand the consequences of their decisions.
Summary: Using a software tool will not only make the learning process more interactive and practical but also provide students with valuable skills that are highly relevant in the project management industry.

## Slide 38
08
HS2061 Information Systems Project Management
Sessions 3 & 4 – Tutor Dr. Farshid Keivanian
These activities are designed to make the class engaging, encourage collaboration, and provide practical experience with key concepts in project time management.
Happy A Learning Day!
Lecturer/Tutor: Dr. Farshid Keivanian